## Template
Group Name |  | Start Date: | 2016-09-13
Team 3
Task | Start Date | End Date | Duration (days) | Percent Complete
1.0 Planning | 2016-09-13 | 2016-09-19 | 6 | 0%
1.1 Subtask 1 | 2016-09-13 | 2016-09-18 | 5 | 0%
Come up with an idea, name for the project, Design, and outline
1.2 Subtask 2 | 2016-09-19 | 2016-10-08 | 19 | 0%
The group decided on tasks and distributed them between members of the group according to their skills and knowledge.
2.0 Analysis | 2016-10-08 | 2016-10-26 | 18 | 0%
2.1 Subtask 1 | 2016-09-17 | 2016-10-05 | 18 | 0%
The time for group members to review Javascript, Html, CSS, and other skills they needed to work on the project
2.2 Subtask 2 | 2016-09-19 | 2016-09-26 | 7 | 0%
The time for group members to review Javascript, Html, CSS, and other skills they needed to work on the project
3.0 Design | 2016-09-24 | 2016-10-09 | 15 | 0%
3.1 Subtask 1 | 2016-09-24 | 2016-10-09 | 15 | 0%
The outline of the website was created. We Planned the layout and the approximate coding needs.
3.2 Subtask 2 | 2016-09-26 | 2016-10-03 | 7 | 0%
Or designer and photograph shared his ideas with the group. A certain plan on the designed was accepted.
4.0 Implementation | 2016-10-01 | 2016-10-15 | 14 | 0%
4.1 Subtask 1 | 2016-10-01 | 2016-10-15 | 14 | 0%
A wrote the HTML code, B wrote the Javascript codes.
4.2 Subtask 2 | 2016-11-01 | 2016-11-30 | 29 | 0%
HTML pages were done, javascript gallery ready. This part was to get everything together and crash the stuff. Errors and weak sides were edited and fixed.
5.0 Testing
5.1 Subtask 1 | 2016-11-01 | 2016-11-30 | 29 | 0%
HTML pages were done, javascript gallery ready. This part was to get everything together and crash the stuff. Errors and weak sides were edited and fixed.
6.0 Deployment
6.1 Subtask 1 | 2016-11-30 | 2016-12-11 | 11 | 0%
The JavaScript gallery was a complete mess, A and B decided to change it to JQuery. A was also doing the CSS.
6.1 Final Task 2 | 2016-12-11 | 2016-12-18 | 7 | 0%
JQuery inserted, CSS ready, The core of the website was ready, only the presentarion left.
Help:
- Go to File => Make a copy... to copy this file to your own Google Docs folder for editing. - Share it with kxaydin@gmail.com